## Final Attachment
Grant** | DEP District | Applicant | Enrolled Site Name | Property Category | Facility/Site ID | Federal FY of Comple-tion* | All SRCOs (including with and without controls) | Acreage*** | SRP Activity Conducted | Status | Property in Reuse | Type of Controls
SRP03 | NW | City of Chipley | City of Chipley Industrial Park and Former City of Chipley Landfill | SW | COM_192756 BF300201000 | 04 |  | Industrial Park - 59; Landfill - 22; Additional parcel - 10 | Assessment | No BSRA implemented. Phase II completed Oct. 2004. No further work recorded according to OCULUS.
SRP03 | NW | Tallahassee Residence Inn, LLC | Residence Inn | Other - Hazardous Substances | BF370002001 | 06 | SRCO with Controls March 19, 2007 | 2.2 | Removal | Last IC/EC Auditing Report completed Nov. 2018. | Hotel | IC, EC
SRP03 | NW | Urban Organics | Former Coca Cola Plant | SW | BF370002002 | 06 |  | 1.6 | Assessment | SRCR requested Jan. 2017.
SRP03 | NW | City of Tallahassee | Salie Property | Other - Hazardous Substances | COM_305296 BF370002003 | 06 | SRCO September 28, 2012 | 2.2 | Phase II Assessment and Removal | SRCO September 2012 | Commercial and residential | No controls required
SRP03 | NW | Brown Barge Middle School | Brown Barge Middle School | Other - Hazardous Substances | COM_145023 | 03 | SRCO with Controls April 3, 2015 | 7.25 | Assessment | SRCO with Controls April 2015 |  | EC
SRP03 | NW | TEAM Santa Rosa Development Council | Santa Rosa Industrial Park | Other | COM_303626 | 06
| NW |  | Plat 1 | Other |  |  |  | 8 | Phase I Assessment | Owned by the County. Phase I completed with no RECs.
| NW |  | Plat 2 | Other |  |  |  | 6 | Phase I Assessment | Owned by Barron Rentals, LLC. Phase I completed with no RECs. | Zoned Light Manufacturing
| NW |  | Plat 3 | Other |  |  |  | 14 | Phase I Assessment | Owned by Pro-Build Real Estate Holdings. Phase I completed with no RECs. | Zoned Light Manufacturing
| NW |  | Plat 4 | Other |  |  |  | 10 | Phase I Assessment | Owned by the County. Phase I completed with no RECs.
| NW |  | Plat 5 | Other |  |  |  | 25 | Phase I Assessment | Owned by Woodstone Enterprises LP. Phase I completed with no RECs. | Warehousing
| NW |  | Plat 6 | Other |  |  |  | 27 | Phase I Assessment | Owned by Milton UTF, LLC. Phase I completed with no RECs. | Warehousing
| NW |  | Plat 7 | Other |  |  |  | 18 | Phase I Assessment | Owned by the County. Phase I completed with no RECs.
| NW |  | Plat 9 | Other |  |  |  | 12 | Phase I Assessment | Subdivided and sold to three property owners. Phase I completed with no RECs. | CNC Machining, Ropella and Associates Search Firm, and Meltpro glue gun assembly.
| NW |  | Plat 10 | Other |  |  |  | 50 | Phase I Assessment | Phase I completed with no RECs.
| NW |  | Plat 11 | Other |  |  |  |  | Phase I Assessment | Phase I completed with no RECs.
SRP03 | NW | Wayne Dalton | Wayne Dalton Corporation (Century Florida) | Other - Hazardous Substances | COM_67838 | 07 | SRCO with Controls June 24, 2009 | 37 | Removal | SRCO with Controls June 2009 | Abandoned facility. No redevelopment as of January 2018. | IC, EC
SRP03 | NW | Sylvania Heights Front Porch, Inc. | Lovejoy Community | Other | COM_303625 BF461001000 | 09 |  | Community-wide, no acreage given | Phase I Area-wide Inventory | Area wide inventory completed, and City has approved a BF area designation. Community representatives still pursuing an EPA enviromental justice grant.
SRP03/SRP09 | NW | New Horizons of Northwest Florida, Inc. | Northview Community Center | UST | COM_214998 | 10 | SRCO with Controls May 25, 2012 | 2.82 | Removal | SRCO with Controls May 2012 |  | IC
SRP09 / SRP18 | NW | Escambia County, Escambia County School District, and City of Pensacola | Maggie’s Ditch | Other - Hazardous Substances | COM_296301 | 11 | Elementary School project portion given an SRCO 7/510. ECSD Outparcel section given SRCO 10/8/13 | 9 | Assessment | School parcel given an SRCO July 2010. RAP approved 2012. Source Removal conducted in June 2013. Phyto-remediation ongoing as of 4/1/19. Further work under SRP Program to begin Nov/Dec 2019.
SRP09 | NW | School District of Escambia County | Brentwood Elementary | Other - Hazardous Substances | COM_189623 | 13 | SRCO issued March 13, 2014 | 7.73 | Removal | SRCO with Controls March 2014 | Continuous use as a school | IC, EC
SRP13 | NW | City of Carrabelle | Former Carrabelle Water Plant | Unknown | COM_333630/ERIC_5556 | 17 |  | 5 | Phase II Assessment and Removal | Excavation complete and add'l assessment performed in Dec. 2017. Title Search ongoing.
SRP13 | NW | TMH Foundation | 107 West College St. | Other - Hazardous Substances | COM_337121 | 15 | Comfort Ltr October 2015 | 0.5 | Assessment | Comfort Ltr October 2015 | vacant bldg
SRP13 | NW | Escambia County School Board | Corner of Spring and Garden Street | Other - Hazardous Substances | ERIC_5558 | 17 | Conditional SRCO issued Oct. 22, 2018. | 2.5 | Removal | Conditional SRCO issued Oct. 22, 2018. | vacant bldg and parking lot | IC, EC
SRP13 | NW | Town of Esto | Former Lamb's Recycling | Unknown | ERIC_7390 | 18 |  | 4.32 | Assessment and Removal | Ph. I & II Assessments tasked Dec. 2017 but cancelled in March 2018 due to site access issues.
SRP13/SRP18 | NW | City of Pensacola | Maritime Park Marina Piling Removal | Other | ERIC_7389/COM_363678 | 19 |  | Unknown | Removal | Cost estimate has been developed but not tasked as of 03/20/19. Removal to begin week of May 6, 2019.
SRP03 | NE | Clara White Mission | Clara White Mission | Other - Hazardous Substances | COM_288316 | 07 | SRCO May 8, 2008 | 0.25 | Removal | SRCO May 2008. |  | No controls required
SRP03 | NE | City of Gainsville, CSX/Rinker Property | Former CSX/Rinker Property (Gainesville Regional Utilities [GRU]) | Other - Hazardous Substances | COM_240844 | 09 |  | 2.77 | Phase II Assessment and Supplemental Assessment | FDEP assessment project completed 2015 and PARM completed January 2016. | Redeveloped into Depot Park
SRP03 | NE | Second Chance Help Center, Inc. | Phoenix Rising Development Parcel | Other - Hazardous Substances | COM_303630 | 07 |  | 5 | Assessment | FDEP assessment project completed. Cleanup is expected to be extensive and costly. Property owner is pursuing additional grant funding options.
SRP03 | NE | City of Gainesville | Airport Industrial Park | Other - Hazardous Substances | COM_101514 | 07 |  | 25 | Assessment | Project completed 2008. Ground water contamination caused by offsite source and is being addressed by responsible party.
SRP03 | NE | City of Gainesville | Depot Park | Other - Hazardous Substances | COM_223909 | 09 |  | 38 | Assessment | FDEP assessment project completed 2009.
SRP03 | NE | City of Jasper | Hobgood/ESP Warehouse | UST | COM_239374 | 09 |  | 2 | Assessment and Removal | Year 7 NAMR completed July 2018.
SRP03/SRP09 | NE | GCS Downtown Phase I, LLC | Green Cove Springs Downtown | Other - Hazardous Substances |  | 09
| NE |  | Parcel A | Other - Hazardous Substances | COM_287782 BF100501001 | 09 | SRCO February 5, 2010 | 2.15 | Removal | SRCO February 2010 |  | No controls required
| NE |  | Parcel B | Other - Hazardous Substances | COM_287186 BF100501002 | 09 | SRCO July 19, 2012 | 1.69 | Assessment | SRCO July 2012 |  | No controls required
| NE |  | Parcel C | Other - Hazardous Substances | COM_287187 BF100501003 | 09 | SRCO June 21, 2013 | 1.73 | Assessment | SRCO June 2013 |  | No controls required
SRP09 | NE | Grace & Truth CDC | Grace and Truth CDC | Other - Hazardous Substances | COM_301848 | 11 | NFA possible in 2016 | 6 | Assessment, Supplemental Assessment, Interim Removal, and Source Removal | Supplemental Assessment and source removal fieldwork complete. Final assessment and removal report received. Project complete. NFA possible in 2016
SRP09 | NE | Hart-Epstein Enterprises, LLC | Former Metter Auto Parts | Other - Hazardous Substances | COM_76633 | 10 |  | 7 | Assessment and Removal | FDEP assessment and limited source removal project completed 2010. DRC under review as of March 2019.
SRP09 | NE | Pamela Hood | Hood Former Gas Station Site | UST | COM_303632 | 11 | Tank Closure Report issued June 2011 | 2.08 | Removal and Assessment | Tank Closure Report issued June 2011 |  | No controls required
SRP09 | NE | Bay Street Station, LLC | Bay Street Station | Other - Hazardous Substances | COM_322919 | 09 | SRCO April 2018 | 4 | Assessment and Feasability Study | Property purchased June 2016 and is now part of Lofts at LaVilla (COM_345271). BSRA executed December 2016. SRCO April 2018. | Multi-family residential properties | IC
SRP09 | NE | Florida Endowment Foundation for Florida’s Graduates | Dee Dee’s Bar Site | UST | COM_306752 / 9503017 | 12 | SRCO September 2012 | 0.7 | Removal | SRCO September 2012 |  | No controls required
SRP09 | NE | Flagler County Free Clinic | Former Bunnell Hospital | Other | COM_315385 | 13 |  | 1.7 | Phase I Assessment | Phase II fieldwork completed in May 2013. Absestos assessment recommended. Follow-up work being considered by county under EPA grant.
SRP09/SRP13 | NE | Destined for a Change, Inc. | American Celcure | Other - Hazardous Substances | COM_69558 ERIC_5566 ERIC_3869 | 11 |  | 2.89 | Assessment and RAE | FDEP assessment and removal project completed as of March 2018. Remedial Action Plan to address contaminated soils approved by District. RAP to be implemented as part of redevelopment of property.
SRP13/SRP18 | NE | Gilchrist County | Former Colt's Station | UST/AST | ERIC_5564 | 19 |  | 1.13 | Assessment and Removal | Supplemental SAR completed in March 2019.
SRP13/SRP18 | NE | Dinesti'a Holdings, LLC | Former Byrd & Son's | Unknown | ERIC_7384 | 19 |  | 0.42 | Assessment | Qtr. 3 Groundwater Monitoring and SRCR completed March 2019.
SRP03 | C | Daytona Beach | Volusia County School Board Property (Former Clyde Morris Landfill) | SW | COM_274071 BF640401001 | 05 |  |  | Assessment | The site is under a BSRA and is currently in remediation.
SRP03 | C | The Center for Affordable Housing, Sanford | Cedar Avenue Properties | UST | COM_274061 | 07 | SRCO July 1, 2008 | 0.68 | Assessment & Removal | SRCO July 2008 | Redevelopment of affordable housing completed. | No controls required
SRP03 | C | City of Winter Garden | Gray Line Trucking Assessment | UST / Other - Hazardous Substances) | COM_239358 BF480201001 | 06 | SRCO July 17, 2017 | 5 | Phase II Assessment and Removal | PRFBSR implementing BSRA. Currently in remediation. City submitted application for a 104(k) grant for cleanup assistance. SRCO July 2017
SRP03 | C | Orange County | Hal Scott Preserve | Other - Hazardous Substances | COM_283130 | 07 |  | 8 | Assessment | Assessment project completed. County elected not to purchase property due to the cost of cleanup.
SRP03 | C | Orange County | Orange Blossom Trail Parcel | UST | Facility ID 488513373 | 09 | SRCO October 15, 2010 | 0.67 | Assessment & Removal | SRCO October 2010 | After removal, parcel purchased by Burger King Corporation. Redevelopment on hold due to economic conditions. | No controls required
SRP03/SRP09 | C | Metro Orlando Affordable Housing | Former Sanford Dry Cleaners | Other (has subtances) | COM_149174/ERIC_5488/ERIC_3947 | 08 |  |  | FDEP assessment project cancelled. | Reconnaissance completed. Project cancelled because responsible party did not obtain funding to proceed with cleanup and redevelopment. Site being cleaned up by EPA under Superfund program.
SRP09 | C | Mobility Scooter Center | Mobility Scooter Center | UST | COM_298762 BF050802001 | 09 |  | 8 | Assessment and RAE | Assessment and Remedial Alternative Evaluation complete. The applicant has entered into a BSRA under the state Brownfields Program.
SRP09 | C | New Smyrna Beach Community Redevelopment Agency | Former Dunn Lumber | Other - Hazardous Substances | COM_270986 | 12 | SRCO December 8, 2016 | 0.85 | Removal | Limited Source Removal completed December 2011. SRCO December 2016
SRP09/SRP13 | C | Firefly Corners, LLC | Former Daniels Publishing | Other - Hazardous Substances | COM_283795 BF480703001 | 12 |  | 1.85 | Removal | Limited Source Removal completed June 2012. Currently undergoing groundwater monitoring.
SRP13 | C | City of South Daytona/First Service Holding, LLC c/o PNC Bank | Former 3-D Oil Site | Other - Hazardous Substances | ST 64/8517537/ERIC_5549 | 18 |  | 0.5 | Removal and Supplemental Assessment | SSAR completed July 2018. Possible SRCO in 2019.
SRP13 | C | Carolyn J. Hughey | Brisson Ave. |  | COM_124508/ERIC_5591 | 15 |  | 18.58 | Assessment and RAE | Site Assessment Report with RAE completed in April 2015. A Report Addendum was issued in October 2015 that detailed supplemental sampling performed in September 2015.
SRP13 | C | Titusville Rifle and Pistol Club | Titusville Rifle and Piston Club | Other - Hazardous Substances | ERIC_5555 | 17 |  | 40 | Assessment and Removal | Limited Scope Source Removal completed in July 2017 and report finalized. No further work expected.
SRP13 | C | City of Apopka | 46 W. Station St. | Other - Hazardous Substances | ERIC_5557 | 16 |  | 0.87 | Assessment | Phase I and Phase II Assessments were completed in June 2016 and showed no contamination concerns.
SRP13 | C | Health Care Center for the Homeless | Former House of Brick | Other - Hazardous Substances | COM_356924 | 17 |  | 2.59 | Removal | Work Plan completed May 2017. After careful review, EPA cancelled the project.
SRP13/SRP18 | C | City of Ocala | Former Royal Oak | Other-Hazardous Substances | COM_27173/ERIC_5565 | 19 |  | 24.28 | Assessment and Removal | Major assessment completed in early 2018. Possible further assessment under SRP in federal FY19.
SRP13/SRP18 | C | Brevard Co. Solid Waste Management Dept. | US 192 SWM Facility - Former Deseret Ranch Cattle Pesticide Application Area | Other - Hazardous Substances | COM_312749 | 19 |  | Approx. 5 | Assessment and Removal | Supplemental SAR tasked in February 2019.
SRP13/SRP18 | C | Volusia County | Former Beck's Ranch | Other - Hazardous Substances | COM_299347 | 19 |  | 25 | Assessment | Supplemental SAR is currently tasked.
SRP03 | SW | City of Tampa | 12th Street Maintenance Yard | UST / Other - Hazardous Substances) | COM_170685 | 05 | SRCO with Controls November 3, 2011 | 7.5 | Removal | SRCO with Controls November 2011 | Property has been redeveloped as affordable apartment housing. | IC, EC
SRP03 | SW | Saddlebag Lake Owners Association | Saddlebag Lake Resort | UST | COM_163104 | 06 | SRCO September 2006 | 0.5 | Removal | SRCO September 2006 | Site already developed | No controls required
SRP03 | SW | City of Tampa | West La Salle Street Property | UST | COM_216696 | 06 |  | 0.67 | Assessment | City implementing RAP. | Continuing site rehabilitation
SRP03 | SW | Tampa Port Authority | Gulf Marine Repair | Other - Hazardous Substances | COM_193206 | 07 |  | 5.84 | Assessment | PRFBSR implementing BSRA? | Coninuing site rehabilitation
SRP03 | SW | City of Temple Terrace | North 56th Street, Terrace Plaza, Bullard Parkway | Other | COM_288585 | 07 | SRCO July 2013 | 35 | Assessment | SRCO July 2013
SRP03 | SW | City of Lake Wales | Oak Ridge Dry-cleaning Plant | Other (has subtances) | COM_283464 | 07 |  | 0.4545 | Assessment | Phase II assessment completed in 2007. No updates found in OCULUS.
SRP03 | SW | City of Tampa | East Tampa/34th Street Property | UST | COM_82602 | 08 | NFA May 2008, did not issue SRCO | 0.03 | Removal | NFA May 2008, did not issue SRCO | Currently a commercial granite/stone business | No controls required.
SRP03/SRP09 | SW | City of Clearwater | City of Clearwater Park | Other - Hazardous Substances |  | 09 |  | 37 | Kickoff meeting | Kick-off meeting held January 20, 2009. Application withdrawn by City and project cancelled.
SRP03/SRP09 | SW | Bay City Elks Lodge #268 | Bay City Elks | UST / Other - Hazardous Substances) | COM_303526 | 10 | No OCULUS updates since 2010 | 0.25 | Assessment and Remediation | No OCULUS updates since 2010
SRP09 | SW | Cigar City Investment Company | Cigar City Site | UST | COM_303528 | 10 | SRCO April 2012 | 0.31 | Assessment and Removal | SRCO April 2012 | Vacant lot | No controls required.
SRP09 | SW | Manal Oil, Inc. | 1310 Cleveland Street aka Manal Oil | UST | COM_184005 | 10 |  | 0.258 | Removal | Removal is complete. Monitoring ongoing as of April 2019. | Owner has completed building construction for a retail center.
SRP09 | SW | City of Tampa | Keen's Corner/Rails to Trails | Other - Hazardous Substances | COM_301887 | 11 |  | 14.24 | Assessment | Supplemental Assessment Report completed March 2011.
SRP09 | SW | City of Arcadia | Former Arcadia State Livestock Market | Other - Hazardous Substances | COM_307202 | 12 |  | 6.5 | Assessment | Assessment completed June 2012.
SRP09 | SW | GRW Holdings, LLC | Paone Site | Other - Hazardous Substances | COM_70228 | 11 |  | 0.3 | Assessment and RAE | Assessment and Remedial Alternatives Evaluation complete. Property owner will need to implement corrective actions.
SRP13 | SW | Daniel A. Ryan | Former Dan Ryan's Corner Septic Systems | UST / Other - Hazardous Substances) | COM_169699 | 13 |  | 1 | Removal | Limited Source Removal to address abandonded USTs completed in 2013.
SRP13 | SW | City of Wauchula | City of Wauchula ROW | Other - Hazardous Substances | COM_315626 | 15 |  | 1 | Removal | Limited Source Removal project completed by FDEP in September 2014. BSRA executed in 2015. Currently under monitoring as of April 2019.
SRP09/SRP13/SRP18 | SW | Gateway Holdings, LLC | Gateway Holdings Property | Other - Hazardous Substances | COM_315712 | 19 |  | 0.4 | Removal | Supplemental SAR completed December 2018. Site turned over to SWD for completion.
SRP13 | SW | Hideaway Hills MHP, LLC | Avalon Inn | UST / Other - Hazardous Substances) | COM_347598/ERIC_5563 | 18 |  | 0.32 | Removal | UST abandoned-in-place in Feb 2018. SSAR completed in Oct 2018. Site to be turned over to district.
SRP13 | SW | Pinellas County | 126th Ave. Landfill | SW | ERIC_5552 | 17 |  | 15 | Removal | Final Completion Report issued February 2017.
SRP13 | SW | Bob Lee's Automotive Repair | Bob Lee's Automotive Repair | Other - Hazardous Substances | COM_350825/ERIC_5554 | 18 |  | 0.25 | Assessment | LSR completed in 2017 and PARM performed for one year. Site being turned over to district.
SRP13 | SW | City of Gulfport | Tangerine Greenway | Other-Hazardous Substances | COM_361307/ERIC_6491 | 18 |  | 5.8 | Assessment and Removal | SSAR performed under SRP13 in Feb. 2018. City is funding ISR and ECMP.
SRP13/SRP18 | SW | UACDC | UACDC | Other-Hazardous Substances |  | 19 |  | 25 | Assessment | Phase I ESA for Group B sites completed in March 2019.
SRP03 / SRP13 | S | Habitat for Humanity Key West and Lower Keys | Former Baltuff Dump Site | SW | COM_297705/BF440701001/ERIC_5553 | 17 |  | 14.25 | Removal | Preliminary Ecological Risk Assessment completed March 2017. Ecological Risk Assessment completed September 2017. No longer in SRP program.
SRP03 | SE | Broward County | East Coast Asphalt Plant | UST | COM_328159 | 04 |  | 4.7 | Assessment | Owner currently working with Petroleum Program.
SRP03 | SE | City of Miami | Former Coleman's Service Station | UST | COM_303628 | 05 |  | 0.27 | Phase II Work Plan | Project cancelled due to property ownership dispute.
SRP03 | SE | A.G. Holley | A.G. Holley Hospital | Other - Hazardous Substances | COM_49478 COM_203777 | 05 | SRCO issued Oct. 19, 2011 | 144.11 | Assessment | SRCO issued Oct. 19, 2011
SRP03 | SE | AR & J Sobe, LLC/ Potamkin Properties | South Beach Properties | UST / Other - Hazardous Substances) | BF130001001 | 06 | SRCO with Conditions March 14, 2012 | 2.85 | Removal | SRCO with Conditions March 2012 |  | IC, EC
SRP03 | SE | City of Ft. Lauderdale/Durrs Homeowner Association | Lincoln Park/Durrs Neighborhood | Other - Hazardous Substances | COM_211581 | 07 |  | 40 | Assessment | Work on DRC ongoing.
SRP03 | SE | City of Boynton Beach | Boynton Beach Landfill and Golf course | SW | COM_295074 | 07 |  | 40 | Assessment | Monitoring ongoing. | Possible redevelopment as solar energy generation plant
SRP03 | SE | Pompano Beach Community Redevelopment Agency | Salley Property | Other - Hazardous Substances | COM_302382 | 09 |  | 0.46 | Assessment and Removal | FDEP Assessment and removal completed.
SRP03 | SE | Pompano Beach Community Redevelopment Agency | B-T Oil Property | UST | COM_302477 | 09 |  | 0.35 | Supplemental Assessment | FDEP Assessment completed.
SRP09 | SE | Goldstein Brownfields Group, Inc. | Former Servico Landfill | SW | COM_299990 BF501501001 | 09 |  | 8 | Assessment | FDEP assessment project completed. DRC signed 01/24/19.
SRP09/SRP13 | SE | Delray Beach CRA | Carver Square | Other - Hazardous Substances | COM_291722 | 13 | SRCO without conditions November 17, 2014 | 2.35 | Assessment and RAE | Source Removal activities completed May 2013. SRCO November 2014 |  | No Controls Required
SRP13 | SE | Martin County BOCC | Future Transit Depot Site | Other - Hazardous Substances | COM_318713 | 14 |  | 2.2 | Removal | Limited Scope Source Removal Report completed December 2013. Recommended Martin County to implement ground water monitoring.
SRP09 | SE | City of Miami Gardens | 1050 NW 163rd Drive | Other - Hazardous Substances |  | 15 |  | 1 | Assessment and RAE | Project cancelled.
SRP09 | SE | The Progressive Civic League of Gifford, Inc. | Gifford Storage Facility | Other - Hazardous Substances | COM_303080 | 11 |  | 0.21 | Assessment and Removal | Limited Scope Phase II Site Assessment and Source Removal Report completed by FDEP June 2011.
SRP13 | SE | City of Boynton Beach | Boynton Beach Town Square | Other-Hazardous Substances | ERIC_5550 | 18 | SRCO without conditions September 28, 2018. | 15.1 | Assessment and Removal | SRCO without conditions September 28, 2018.
BF - Brownfields
BSRA - Brownfield Site Rehabilitation Agreement | [5 empty] | NFA - No Further Action |  |  |  |  | VCP - Voluntary Cleanup Program
EC - Engineering Controls | [5 empty] | O - Other |  |  |  |  | RAP - Remedial Action Plan
FF - Federal Facilities | [5 empty] | PRFBSR - Person Responsible for Brownfield Site Rehabilitation
FPS - Federal Program Section | [5 empty] | RECs - Recognized Environmental Conditions
HW - Hazardous Waste Facility | [5 empty] | RECs - Recognized Environmental Conditions
IC - Institutional Controls (deed restrictions) | [5 empty] | SF - Superfund
NAM - Natural Attenuation Monitoring | [5 empty] | SRCO - Site Rehabilitation Completion Order
NEPA - National Environmental Policy Act | [5 empty] | SW - Solid Waste
UST/LUST - Underground Storage Tank/Leaking Underground Storage Tank
*Year provided is for completion or projected completion of SRP Activities
**Grant key: |  | SRP03 - RP97484603
SRP09 - RP95439509
SRP13 - RP00D13513
*** Total number of acres associated with site.