## Slide 1: PETROLEUM RESTORATION PROGRAM PRP Site Managers Workshop Orlando, Florida
Division of Waste Management
PETROLEUM RESTORATION PROGRAM
PRP Site Managers Workshop
Orlando, Florida
March 25 - 26, 2014

## Slide 2: INTRODUCTION AND WELCOME DAY 1
March 25-26, 2014 |  | 
PRP Site Managers Workshop |  | 
FLORIDA MALL HOTEL, ORLANDO, FLORIDA |  | 
Time | Topic | Speaker
 | DAY 1 (Tuesday, March 25, 2014) | 
1:00 - 1:15 pm | Introduction and Welcome | Valerie Huegel
1:15 - 1:45 pm | The Evolution of PRP and Procurement | Diane Pickett
1:45 - 3:00 pm | Procurement Workflow Overview | Kyle Kilga
3:00 - 3:15 pm | Break | 
3:15 - 4:15 pm | Scope of Work (SOW) Development | Rickey Beasley
4:15 - 5:15 pm | Three Separate Round Table Discussions | 
 | Site Assessment (PG) | Busen
 | Site manager (SM) | Kilga, Beasley, Rivera
 | Local Program Managers Only | Huegel, Pickett

## Slide 3: INTRODUCTION AND WELCOME DAY 2
 | DAY 2 (Wednesday, March 26, 2014) | 
 | Site Management Training | 
8:00 - 8:30 am | ATCs - Direct Assign and RCI | Kyle Kilga
8:30 - 9:00 am | PR/PO w/MFMP | Rickey Beasley
9:00 - 9:30 am | Activities and Deliverables/Submittals | Kyle Kilga
9:30 - 10:00 am | Invoicing and Change Orders | Kyle Kilga
10:00 - 10:15 am | Break | 
10:15 - 10:45 am | STCM/OCULUS | Grace Rivera
 | Site Closure | 
10:45 - 11:00 am | Site Conceptual Model/Remedial Strategies | John Wright
11:00 - 11:15 am | Risk Based Closure Options | John Wright
11:15 - 11:30 am | LSSI Closures | Diane Pickett
11:30 - 11:45 am | IC Process & FDOT MOU | John Wright
11:45 - 12:00 pm | Closure Sampling Guidelines | Diane Pickett
12:00 - 12:15 pm | Questions and Answers | All
12:15 - 1:30 pm | Lunch | 
1:30 - 1:40 pm | Cost Shares - PAC, PCPP, SRFA | Ken Busen
1:40 - 2:00 pm | Site Inspection - Assessment and Remediation Sites | Ken Busen
2:00 - 2:15 pm | Break | 
2:15 - 3:15 pm | Remediation (PE) round table discussion | Wright
3:15 pm | Adjourned | 

## Slide 4: Petroleum Restoration Program
Petroleum Restoration Program
Valerie K. Huegel
Administrator
Petroleum Restoration Program
Division of Waste Management
Site Manager Workshop
March 25, 2014

## Slide 5: Program Status and Total Expenditure
As of March 2014:
Eligible sites cleaned up 7,258 Eligible sites underway 3,167 Eligible sites awaiting clean up 6,911
=====
Approximate number of total sites eligible for state funding 17,336
Approximately $2B spent on site cleanup since program inception in 1986.
FY 2013-14 appropriation is $125M

## Slide 6: Proviso and Implementing Bill
The Proviso and Implementing Bill provided up to $50 million to fund task assignments, work orders and contracts entered into prior to June 30, 2013.
After June 30, 2013, the Department could only enter into competitively procured contracts.
The balance of appropriation ($75M) would be subject to approval by the Legislative Budget Commission.

## Slide 7: LBC Approval
The LBC met on September 12, 2013, and approved our plan to move forward which included a transition to:
  Continue to procure work competitively using the $50M initially appropriated.
  Adopt rules.
  Divest the Department from ownership of remedial systems whose maintenance was costing >$250,000 per year.
  Secure Agency Term Contractors.

## Slide 8: Current Program Status
Obligated the totality of $50M.
Completed rulemaking.
Completed the first phase of equipment divestiture.
Entered into contract with Agency Term Contractors (“Contractors”).
Worked very closely with House staff on a draft Petroleum Bill that codifies our reforms by removing any reference to the former “pre-approval” program.

## Slide 9: Rulemaking
Two new rules: 62-771 and 62-772.
62-771: revises site scoring.
62-772: codifies procurement.
Both adopted on 12/27/2013.
These rules do not reduce standards of protection.
Worked in close coordination with all stakeholders and adopted without protest.

## Slide 10: Procurement of Contractors
10/3/2013: Invitation to Negotiate (ITN) issued.
1/14/2014: 70 vendors qualified for negotiations.
2/3/2014 to 3/1/2014: Contract negotiations.
3/24/2014: All but four JV contracts executed.
Approximate average savings of 20% in unit rates for most activities.

## Slide 11: Contractor Task Assignment
Contractors are assigned tasks without staff bias for or against any contractor.
Work assignment follows an algorithm based on three variables: Bonding Capacity, Encumbered Balance, and Schedule Rank (Relative Capacity Index).
Contractor performance is key to reduce their encumbered balance so it can be assigned additional tasks.

## Slide 12: Conclusions
The Department has addressed all aspects of the Proviso and Implementation Bill.
Program is focused on achieving aggressive procurement and performance goals
It has worked collaboratively with all stakeholders.

## Slide 13: Questions
Valerie K. Huegel
valerie.huegel@dep.state.fl.us
(850) 245-8821
Diane Pickett, P.G.
diane.pickett@dep.state.fl.us
(850) 245-8893
Kenneth Busen, P.G.
kenneth.busen@dep.state.fl.us
(850) 245-8745
John Wright, P.E.
john.wright@dep.state.fl.us
(850) 245-8888
Grace Rivera
grace.rivera@dep.state.fl.us
(850) 245-8882
Rickey Beasely
Rickey.beasely@dep.state.fl.us
(850) 245-7619
Kyle Kilga
kyle.kilga@dep.state.fl.us
(850) 245-8855
QuestiQuestionsons?
Notes: We will be very glad to answer any questions you may have.

## Slide 14: Competitive Procurement
Thru competitively procured contracts with qualified responsive & responsible contractors
Kyle Kilga
Petroleum Restoration Program
March 25, 2014

## Slide 15: Procurement Procedures for Petroleum Cleanup Chapter 62-772 F.A.C.
To establish a competitive procurement process for petroleum cleanup and improve the efficiency of the Petroleum Restoration Program
Applicable to site remediation work on sites eligible for state funding from the Inland Protection Trust Fund
Assignment thru formal contract, task assignment or Department issued purchase order

## Slide 16: Procurement Methods
eQuote
Invitation to Bid (ITB)
Invitation to Negotiate (ITN): Agency Term Contractors
  Direct Assignment
  RCI Assignment

## Slide 17: eQuote Procurement
Initially used for site work with projected costs <$35,000
  62 awards totaling $1.16 M
  57-Low-Score Site Assessments (LSA) and 5-Well Abandonment
  PRP developed Scope of Work (SOW) and Task Items
Procured thru MFMP & awarded to lowest qualified quoter
Purchase Requisition (PR) prepared & Purchase Order (PO) issued with designated Task Items and invoicing tied to submission and approval of Task Item Deliverables

## Slide 18: Invitation to Bid (ITB) Procurement
Used for work projected to exceed $35,000
  12 single site awards totaling $1.22M
  RAC, SR, O&M and PT
PRP developed scope of work and rate sheet items
Advertised on Vendor Bid System (VBS) & awarded to lowest qualified bidder
Purchase Requisition (PR) prepared & Purchase Order (PO) issued with designated Task Items and invoicing tied to submission and approval of Task Item Deliverables

## Slide 19: Invitation to Bid (ITB) Procurement continued
Used for bundling sites with same scope of work
  1 bundle of 39 LSA sites (less 2 removed)
  Estimated total of $1.37 M
  ITB included a Generic Scope of Work and a separate Rate Sheet for each site
  Vendors able to submit quote for any or all of the sites
  Each site to be awarded to the lowest qualified quoter
  Still in Procurement Office waiting to be awarded

## Slide 20: Invitation to Negotiate (ITN) Solicitation # 2014004C
ITN Posted for Petroleum Contamination Site Response Action Services (10/3/13)
900+ vendor questions received and answered
Responses due Nov 7th, 14th, or 21st based on region
Department reviewed responses and issued Notice of Intended Award for all 3 regions January 14, 2014
Contract negotiations conducted (2/14/14 to 3/1/14)
Contracts sent to awardees (2/14/14 to 2/28/14)
Joint Venture contract still waiting in Procurement Office

## Slide 21: Invitation to Negotiate (ITN) Solicitation # 2014004C
Agency Term Contract Master Agreements awarded with negotiated rates in designated regions to 72 different contractors and totaling 160 contracts
  North – 48 ATCs
  Central – 57 ATCs
  South – 55 ATCs
Currently 151 contracts executed

## Slide 22: Site Assignment to ATCs
Transition from Preapproval Program work orders to ATC issued purchase orders in MFMP
Direct Assignment / RCI Assignment
Owner/RP will no longer select contractor
  Exception: LSSI or owner cost share 25% or greater
Includes
  PRP developed SOWs and ATC developed SOWs
  Schedule of Pay Items (SPI) which incorporate the ATCs negotiated item rates

## Slide 23: Direct Assignment (DA)
As ATCs are executed, contractors are being assigned 1 to 2 LSA or NAM sites totaling $40-60 K
Additional DAs will include continuation of O&M and PARM sites transitioning from Preapproval
  SOW and SPI prepared by contractor and negotiated with site manager
  PRP Contracting Group inserts ATCs contract rates and prepares PR in MFMP

## Slide 24: Relative Capacity Index (RCI)

## Slide 25: RCI Calculation Elements
Bonding Capacity – The vendor’s most recently demonstrated limits of Performance or Financial Guarantee Bonding
  Bonding Cap Ceiling of $3,000,000
Schedule Rank – rank of the eligible vendors within a given region based on the each vendor’s contracted Schedule of Pay Item Prices for the expected Scope of Work
  Where the resulting lowest Pay Schedule calculated cost is ranked a 1 for the expected work elements

## Slide 26: RCI Calculation Elements Continued
Encumbrance Balance =
        STCM WO/TA encumbrance (exclusions LSSI, PBCs and Cost Shares 25% or greater)
        Plus Change Orders
        Less Invoiced Amounts
        Plus Interim Ledger Amount
  Interim Ledger Amount = dollar amount of work assigned to ATC via DA or RCI Assignments prior to TA approval on BCO Weekly Encumbrance

## Slide 27: RCI Assignment
Currently run via a very elaborate Excel workbook
Ranks ATCs within the region of the site
<$195,000 = Assign to #1 RCI ranked ATC
=>$195,000 = Top 3 (or more) RCI ranked ATCs are invited to review SOW and SPI and submit final bid via MFMP eQuote system
  ATCs may reduce their contract rate for individual SPIs but cannot increase any rates
  Lowest responsive quote will be awarded work

## Slide 28: Workflow

## Slide 29: Workflow

## Slide 30: Questions???

## Slide 31: Scope of Work SOW Development
Rickey Beasley, John Wright & Diane Pickett

## Slide 32: Chapter 287 – Procurement of Personal Property and Services
287.058 Contract document.—
(d) Specifying a scope of work that clearly establishes all tasks the contractor is required to perform.
(e) Dividing the contract into quantifiable, measurable, and verifiable units of deliverables that must be received and accepted in writing by the contract manager before payment. Each deliverable must be directly related to the scope of work and specify a performance measure. As used in this paragraph, the term “performance measure” means the required minimum acceptable level of service to be performed and criteria for evaluating the successful completion of each deliverable.
(f) Specifying the criteria and the final date by which such criteria must be met for completion of the contract.
(h) Specifying the financial consequences that the agency must apply if the
contractor fails to perform in accordance with the contract.

## Slide 33: Components of SOW
Introduction
Site Specific Scope
  Overview
  Detailed Scope of Work
  Identify Specific Task
  Performance Measures
Warranty
Deliverables
Invoicing and Payments

## Slide 34: Introduction
Phase of Work
Site Name
Site Address
Facility Identification Number
Identification of the eQuote, ITB or ATC contract

## Slide 35: Example of an Introduction
This scope of work (SOW) has been prepared for the removal of petroleum contamination associated with the Valero gasoline service station located at 5145 North Highway 17, De Leon Springs (Site). UNIVERSAL Solutions, Inc. (Contractor) has been identified to perform the work. The site is characterized as an imminent threat. The Contractor shall provide all labor, materials, and equipment required to complete all tasks associated with the pre-excavation, excavation, and post-excavation activities as specified below and depicted in the attached figures and tables. The Contractor will be responsible for all work regardless of whether performed by the prime or a subcontractor.
Information on previous site assessment and engineering documents referenced below may be found in OCULUS at http://depedms.dep.state.fl.us/Oculus/servlet/login. Guidance documents referenced in this SOW may be found at the FDEP website Procedures & Guidance Documents, Petroleum Restoration Program at Petroleum Restoration Program Procedures & Guidance Documents | Petroleum Storage Systems | Waste Mgmt | Florida DEP.
The SOW is based on and shall be done in accordance with: (1) the May 1, 2007 Remedial Action Plan Modification (RAPM), inclusive of supplemental information dated through January 2, 2008, for which an Amended RAP Approval Order was issued on February 22, 2008; (2) an already prepared Maintenance of Traffic (MOT) plan for the temporary rerouting of traffic and roadway reconstruction; (3) an important clarification herein regarding the term “phases” (Section 2.2 of this SOW); and (4) information herein that supersedes the dimensions in the approved RAPM that define the remediation zone containing the northbound and southbound lanes (Section 2.2 and Section 4.1.10).

## Slide 36: Site Specific Scope
Overview
Detailed Scope of Work - Must clearly establish all services that the contractor is required to perform
Identify Specific Tasks - Identifying Logical Completion Points for Payments
Performance Measures

## Slide 37: Detailed Scope of Work - Examples
Low Score Assessment (LSA)
Natural Attenuation Monitoring (NAM)
Remedial Action Construction (RAC)
Site Assessment (SA)
Source Removal (SR)

## Slide 38: Warranty
A statement for warranty is used only for RAC’s, RAP’s, SR’s, Dewatering, SA’s, WA and O&M’s SOW
Warranty period must be a year after the end of the project.
Purchase Order will end a Year after the completion of the SOW to cover the warranty period.
Retainage is withheld until the end of the warranty period???

## Slide 39: Warranty Statement
4.0 Warranty
The work shall include a one-year warranty from the date of acceptance of work for all workmanship and equipment provided and installed by the Contractor. The Contractor is responsible for replacing and correcting any defective equipment or failures due to poor workmanship during the one-year warranty period. The warranty period shall survive the term of the MFMP PO. Contractor shall provide a plan of intended repairs or replacements within fourteen (14) days of notification of warranty claim by DEP. Any refusal or failures by the Contractor to replace or correct deficiencies may result in the suspension of all other work assigned under the ATC.

## Slide 40: Deliverables
All deliverables stated must be quantifiable and measurable
A deliverable must be directly related to the SOW
A deliverable is needed for each invoicing point. (Note: All deliverables must be accepted in writing by the Site Manager before payment)

## Slide 41: Performance Measures
Must be directly related to the Task in supporting performance. For example: Source Removal with excavation of 100,000 cy may establish an invoicing and deliverable point at a minimum specified excavation interval of 25,000 cy, with the understanding that the final invoice may be for less than the 25,000.

## Slide 42: Invoice, Payments, Performance Schedule
Identifying major tasks for completion during the project
Establishing reasonable performance periods based on the issuance of a MFMP Purchase Order (PO)
Identifying invoicing and payment opportunities, considering performance measures, for the Contractor and Department to monitor progress
Establishes retainage percentage to be withheld pending completion of the scope.

## Slide 43: Invoice and Payment Example
INVOICING AND PAYMENTS
No invoice will be paid prior to submission and approval of applicable affidavits. Invoices may be submitted upon completion of individual tasks as specified in Section T of this Scope of Work, or not more frequently than every thirty (30) days for completed work. Each invoice request must contain all documentation of performance as specified in the ATC, the applicable Scope of Work, and/or the Schedule of Pay items.
If a deliverable is deemed unsatisfactory the Contractor shall re-perform the work needed to insure satisfactory deliverables, at no additional cost to the Department. Failure to provide all deliverables, or failure to provide deliverables which are satisfactory, or failure to meet the specified deliverable timelines, shall result in non-payment, loss of retainage, or other financial consequences, and/or termination of the Purchase Order, as specified in the ATC.
Retainage shall be withheld in the amount of 10% from each payment by DEP until completion and approval of all tasks. Contractor shall submit Release of Claims and request for retainage with the final invoice. Payment of retainage will be reduced by the amount of any assessed financial consequences.

## Slide 44: Performance/Project Schedule
PROJECT SCHEDULE – Upon Issuance of a MFMP PO by DEP to the Contractor:
Below is the proposedschedule for the project for the items listed below.
MFMP Purchase Order issuance date: Day 1
Completion of Task 1 and delivery of all required affidavits (subject to authority established in Section A), the Historical Summary Worksheet, HASP, proposal with recommended course of action, and the email to DEP regarding Permitting Needs: Day 60
DEP review and comments to the deliverables described in Task 1: Day 74
Submission of the invoice for Task 1: Day 79
If approved by DEP, Task 2 begin date: Day 79
Completion of Task 2 and delivery of the Interim Deliverable to the DEP: Day 168
DEP’s review and response to the Task 2 Interim Deliverable: Day 182
Submission of the invoice for Task 2: Day 187
If approved by DEP, Task 3 begin date: Day 187
Completion of Task 3 and delivery of the TSAR to the DEP: Day 287
DEP’s review and response to the Task 3 TSAR: Day 301
Submission of final invoice and Release of Claims form: Day 306
End date of MFMP Purchase Order: Day 310
It is understood that should the due date for a deliverable fall on a weekend or State observed holiday, the due date will be recognized as the next State business day. This recognition is for both the Contractor and the DEP in meeting the schedule described above.

## Slide 45: Change Order
The Department is considering a process for handling in field change request that must be addressed in order to avoid Contractor down time

## Slide 46: Change Order Language
The proposed schedule may be adjusted if justified. Any request for change must be submitted by the Contractor in writing and approved in writing by the DEP prior to performance of any additional or modified work. The request and approval shall be attached to the MFMP Purchase Requisition to document the approved change.
The MFMP PO issued for this project shall not exceed 310 calendar days from the original date of issuance. Any extension of this term will require issuance of a MFMP PO Change Order. If the Scope of Work described herein is modified for any reason, a MFMP PO Change Order documenting the authorized changes will be issued to the Contractor. The original date of issuance of the MFMP PO will be used to track all deliverable due dates and completion points. However, the Contractor is encouraged to complete all work expeditiously.

## Slide 47: QUESTIONS

## Slide 48: CONCURRENT ROUND TABLE DISCUSSIONS
ASSESSMENTS – PGs
SITE MANAGERS
LOCAL PROGRAM MANAGERS ONLY