## Beach Project List
| Project Name |  | Sponsor | Amount Per LBR (State Share) | Amount Appropriated (State Share) | Amount to be Contracted / Encumbered (State Share) | Executed | Funding Source | Comments
Post Construction Monitoring 2&3yr, work done only in current fy |  |  |  | 3763267 | 1578216 | 1241241.15
Inlet List |  |  |  | 14359316 | 7059250 | 8761736.44
Beach Project List
15DU1 | Duval County Shore Protection Project | D | City of Jacksonville | 31159 | 2031159 | 2031159 | 2015-02-25 | EMTF
11ME1_A2 | Anna Maria Island/ Cortez Groin Replacement & Coquina Beach Nourishment | D/C | Manatee County | 2007250 | 2007250 | 1782250 | 2014-10-02 | GR | Reallocate remaining funds
09SL2 | Ft. Pierce Shore Protection Project | D | St. Lucie County | 166000 | 338000 | 331085.11 | 2014-08-28 | GR | Reallocate remaining funds
| Anna Maria Island/ Manatee County Shore Protection Project | D/C | Manatee County | 2126401
| Gasparilla Island- Lee County Shore Protection Project | D | Lee County | 106822 | 106822 | 0 |  |  | Reallocate all funds
14PB1_A2 | Jupiter/Carlin Segment- Palm Beach County Shore Protection Project | C | Palm Beach County | 1625000 | 1625000 | 1497991.09 | 2015-10-03 | GR | Reallocate remaining funds
14PB3_A2 | North Boca Raton Segment/ Palm Beach County Shore Protection Project | D/C | City of Boca Raton | 1012750 | 351500 | 351500 | 2015-07-24 | EMTF
15PB3 | Ocean Ridge Segment- Palm Beach County Shore Protection Project | C | Palm Beach County | 751300 | 751300 | 751300 | 2015-07-29 | EMTF
14ME2 | Longboat Key Beach Nourishment | C | Town of Longboat Key | 2335034 | 2335034 | 505060 | 2014-12-15 | GR
14ME2_A1 | Longboat Key Beach Nourishment |  |  |  |  | 1829974 | 2016-01-19
11ST1-A2 | Lido Key Beach Nourishment | C | City of Sarasota | 387500 | 3787500 | 3787500 | 2016-01-12 | GR
| Ft. Zachary Taylor Breakwater Rehabilitation | D/C | FDEP-Parks | 1533000
13GU2_A1 | St. Joseph Peninsula Beach Nourishment | D | Gulf County | 230425 | 230425 | 107887.6 | 2015-05-29 | EMTF | Reallocate remaining funds
13GU2_A1 | St. Joseph Peninsula Beach Nourishment | D | Gulf County |  |  | 31080.64
15SL1 | Ft. Pierce Beach Emergency Truck Haul | C | St. Lucie County | 675000 | 675000 | 675000 | 2014-09-18 | EMTF
14CO1_A1 | Collier County Beach Nourishment | C | Collier County | 1621672 | 1621672 | 1621671.51 | 2016-01-19 | EMTF | Reallocate remaining funds
14NA1 | South Amelia Island Beach Nourishment | D/C | FDEP-Parks/SAISSA | 4127584 | 4127584 | 4127584 | 2014-12-03 | GR/EMTF
14ES1 | Pensacola Beach Nourishment | D/C | Santa Rosa Island Authority | 8532302 | 8532302 | 198638 | 2014-12-19 | EMTF
14ES1_A1 | Pensacola Beach Nourishment |  |  |  |  | 7867996 | 2015-09-04 | GR | Reallocate remaining funds
15PB4 | Delray Beach Shore Protection Project | C | City of Delray Beach | 1006016 | 1006016 | 905451.6 | 2015-09-10 | EMTF | Reallocate remaining funds
15PB5 | Delray Beach Shore Protection Project |  |  |  |  | 94668 | 2016-01-05 | EMTF | Reallocate remaining funds
15MI2 | Jupiter Island Beach Nourishment | D/C | Town of Jupiter Island | 1380993 | 1380993 | 1380993 | 2015-12-31 | EMTF
15IR1 | Wabasso Beach Restoration | C | Indian River County | 5650000 | 4969919 | 4969919 | 2015-04-09 | EMTF
15MI1 | Bathtub/Sailfish Point Project | D | Martin County | 125000 | 125000 | 86118 | 2015-07-14 | GR | Reallocate remaining funds
15CO1 | South Marco Island Nourishment | C | Collier County | 233254 | 233254 | 41231.92 | 2016-02-11 | EMTF | Reallocate remaining funds
14BO2_A1 | Segment II/ Broward County Shore Protection Project | C | Broward County | 2036419 | 2036419 | 2036419 | 2016-01-07 | EMTF | Reallocate remaining funds
| Navarre Beach Nourishment | D/C | Santa Rosa County | 4854857
| Long Key/ Upham Beach Groin Replacement | D/C | Pinellas County | 4484000
| Bonita Beach Nourishment | D/C | Lee County | 582574
| South St. Lucie Beach Restoration | C | St. Lucie County | 38271
| Charlotte County Beach Restoration | F/C | Charlotte County | 1041759
| Mid-Town Beach Nourishment | C | Town of Palm Beach | 5531960
| South Siesta Key Beach Nourishment | D/C | Sarasota County | 2963328
| Marathon Beaches Emergency Repair | C | City of Marathon | 20000
| Central Boca Raton Beach Nourishment | D/C | City of Boca Raton | 3887916
| Hallandale Beach Nourishment | D | City of Hallandale | 367536
| Phipps Ocean Park Beach Nourishment | C | Town of Palm Beach | 812370
| Key Biscayne Beach Nourishment | D/C | Village of Key Biscayne | 1075794
| Perdido Key Beach Restoration | C | Escambia County | 5822445
| Hillsboro Beach Nourishment | D | City of Hillsboro Beach | 71151
| South Boca Raton Beach Nourishment | D/C | City of Boca Raton | 1385190
15BE3 | Mid Reach/ Brevard County Shore Protection Project | D | Brevard County | 28360 | 361922 | 199797.53 | 2015-06-08 | gr | Slip remaining funds
| South Palm Beach Island Restoration | F | Palm Beach County | 118703 | [6 empty] | 91
| Coral Cove Park Dune Nourishment | C | Palm Beach County | 470000
| Curry Hammock Beach Restoration | F | FDEP | 75000
| Vero Beach Restoration | F | Indian River County | 50000
|  |  | Beach Erosion Control Program FCO Appropriation | 89504678 | 47271537 | 47215252.59
290360
55988
62500
185000
72540
16158
239195
96708
54706
10476

## Post-Const. Mon
|  | Amount Per LBR (State Share) | Amount Appropriated (State Share) | Amount to be Contracted / Encumbered (State Share) | Executed | Comments
| Anna Maria Island/ Cortez Groin Replacement & Coquina Beach Nourishment | 32500
15SL4 | Ft. Pierce Shore Protection Project | 135000 | 135000 | 135000 | 2015-04-09
| Anna Maria Island/ Manatee County Shore Protection Project | 202104
15BE4 | Brevard County SPP/ North&South Reaches | 321068 | 290360 | 234075.59 |  | Reallocate remaining funds
| Gasparilla Island- Lee County Shore Protection Project | 55988 | 55988 | 0 |  | Reallocate all funds
| Longboat Key Beach Nourishment | 131043
15LE1 | Blind Pass Ecozone Restoration | 62500 | 62500 | 62500 | 2016-02-23 | Reallocate remaining funds
| St. Joseph Peninsula Beach Nourishment | 42895
12MI1_A3 | Martin County Shore Protection Project | 342300 | 185000 | 185000 | 2016-02-14 | Reallocate remaining funds
14CO1 | Collier County Beach Nourishment | 72540 | 72540 |  |  | Reallocate all funds
14NA1 | South Amelia Island Beach Nourishment | 262864 | 93476 | 46711.32 | 2014-12-03 | Reallocate remaining funds
| Pensacola Beach Nourishment | 87700
16MI1 | Jupiter Island Beach Nourishment | 123327 | 41109 | 8378.69 | 2014-12-05 | Reallocate remaining funds
15IR1 | Wabasso Beach Restoration | 1075000 | 225000 | 225000 | 2015-04-09
15CO1 | South Marco Island Nourishment | 16158 | 16158 | 7173.92 | 2016-02-11 | Reallocate remaining funds
| Bonita Beach Nourishment | 13564
15SL3 | South St. Lucie Beach Restoration | 239195 | 239195 | 239195 | 2015-02-26
14CH1_A1 | Charlotte County Beach Restoration | 402746 | 96708 | 61783.13 | 2015-12-10 | Reallocate remaining funds
| Marathon Beaches Emergency Repair | 4500
15DA4 | Key Biscayne Beach Nourishment | 54706 | 54706 | 25947.5 |  | Reallocate remaining funds
| Estero Island/ Lee County Shore Protection Project | 22500
15BO2 | Hillsboro Beach Nourishment | 31428 | 10476 | 10476 | 2015-12-09
| Destin Beach Restoration | 31643
|  | 3763269 | 1578216 | 1241241.15

## Inlet Management Plan
Contract Number | Project Name | Sponsor | Amount per LBR (State Share) | Amount Appropriated (State Share) | Amount to be Contracted / Encumbered (State Share) | Executed | Comments
Inlet Sand Bypassing/Inlet Management Plan Implementation Projects
15BE2 | Port Canaveral IMP Implementation | Canaveral Port Authority | 100500 | 67000 | 67000 | 2014-09-30
15BE2_A1 | Port Canaveral IMP Implementation | Canaveral Port Authority |  |  | 33500 | 2015-12-11 | Provided 75% cost share
14PB7_A2 | Lake Worth IMP Implementation | Town of Palm Beach | 54000 | 36000 | 54000 | 2016-01-05 | Provided 75% cost share
15MI3 | St. Lucie Inlet IMP Implementation | Martin County | 4781250 | 3187500 | 4631779.45 | 2016-01-12 | Provided 75% cost share
| East Pass IMP Update-Norriego Pt. | City of Destin | 3768750 | 3768750 | 3768750 |  | Re-appriated in 15/16
| St. Andrew's Inlet IMP Implementation | FDEP- Parks | 2220000 | - | - |  | Funded outside of program.
| South Lake Worth Inlet IMP Implementation | Palm Beach County | 536250 | - | - |  | Adequate funds in contract
| Sebastian IMP Implementation | Sebastian Inlet District | 153000 | - | - |  | Adequate funds in contract
14ME4_A2 | Longboat Pass IMP Implementation | WCIND, Town and County | 1374866 |  | 142909 | 2016-02-08 | Funded eligible tasks.
15PB6 | Boca Inlet IMP Implementation | City of Boca Raton | 395700 |  | 63797.99 | 2016-03-08 | Funded eligible tasks.
*15PB6 | Boca Inlet IMP Implementation | City of Boca Raton |  |  |  | 2016-03-08 | Balance funded with 13/14 unencumbered funds.
*08ST1_A5 | Venice Inlet IMP Implementation | WCIND | 337500 | - | - | 2016-01-12 | Fully funded with 10/11 unencumbered funds.
*16SL1 | Ft. Pierce Inlet IMP Implementation | St. Lucie County | 450000 | - | - | 2016-03-22 | Fully funded with 10/11 unencumbered funds.
*15ME1 | Southwest Gulf Coast Regional Inlet Study | WCIND | 187500 | - | - | 2016-01-12 | Fully funded with 10/11 unencumbered funds.
|  | 2014/15 Totals | 13384316 | 7059250 | 8761736.44
* Refer to FY2015-16 Financial Summary and Accountability Report
350695.25