## Project List
Contract Number | Project Name | Phase | Sponsor | Amount per LBR (State Share) | Amount Appropirated (State Share) | Appr. Fund | 29 digit funding source code | Amount to be Contracted (State Share) | Scope of Work Approval | Date Draft in Process | Date Forwarded to Sponsor | Date recevied from Loca Sponsor | Date Executed | Comments
Inlet List | No appropriation for Inlets in FY 15-16 |  |  | 9787190 | 0
Post Construction Monitoring 2yr.+ |  |  |  | 2684976 | 1533954
Regional Monitoring |  |  |  | 250000 | 0
Beach Project List
| Venice Beach Nourishment/ Sarasota County Shore Protection Project | C | City of Venice | 1100910.966 | 966046 | GR | 37 10 1 000286 37350100 00 140126 16
| Venice Beach Nourishment/ Sarasota County Shore Protection Project |  |  |  | 134865 | LATF | 37 20 2 423001 37350100 00 140126 16
| Duval County Shore Protection Project | D,C | City of Jacksonville | 726848.4647
| Walton County Hurricane and Storm Protection Project | C | Walton County | 10520989.92
15SL4_A1 | Ft. Pierce Shore Protection Project | D | St. Lucie County | 100000 | 100000 | LATF | 37 20 2 423001 37350100 00 140126 16 | 47472 | 2016-02-12 | 2016-03-08 | 2016-04-01 | 2016-04-06 |  | In draft
| Brevard County Shore Protection Project/ North&South Reaches | D | Brevard County | 39261.6 | 39262 | LATF | 37 20 2 423001 37350100 00 140126 16
| Broward County Shore Protection Project/ Segment III | D | Broward County | 496486.08 | 248243 | LATF | 37 20 2 423001 37350100 00 140126 16
| Blind Pass Ecozone Restoration | D | Lee County | 60000 | 60000 | LATF | 37 20 2 423001 37350100 00 140126 16
16NA1 | South Amelia Island Beach Nourishment | D | FDEP-Parks/SAISSA | 117630 | 117630 | LATF | 37 20 2 423001 37350100 00 140126 16 | 113184.37 | 2016-03-30 | 2016-04-05 |  |  |  | In draft
| Upham Beach Groin Replacement | D,C | Pinellas County | 4566500 | 3000000 | LATF | 37 20 2 423001 37350100 00 140126 16
| Longboat Key Beach Nourishment | D,C | Town of Longboat Key | 1598463.4799 | 1500000 | LATF | 37 20 2 423001 37350100 00 140126 16
| Charlotte County Beach Restoration | F,D,C | Charlotte County | 3561746.926 | 2500000 | LATF | 37 20 2 423001 37350100 00 140126 16
| Nassau County Shore Protection Project | C | City of Fernandina Beach | 107833.68
| Jupiter Island Beach Nourishment | D,C | Town of Jupiter Island | 1615453.2959 | 1000000 | LATF | 37 20 2 423001 37350100 00 140126 16
| North Boca Raton Segment/ Palm Beach County Shore Protection Project | D | City of Boca Raton | 106150
11ME1_4 | Anna Maria Island Cortez Groins Replacement | C | Manatee County | 2845675 | 2500000 | LATF | 37 20 2 423001 37350100 00 140126 16 | 2500000 | 2016-02-10 | 2015-03-25 |  |  |  | In draft
| Collier County Beach Nourishment | C | Collier County | 1526035.386 | 1500000 | LATF | 37 20 2 423001 37350100 00 140126 16
16LE1 | Bonita Beach Nourishment | D,C | Lee County | 693527.32 | 500000 | LATF | 37 20 2 423001 37350100 00 140126 16 | 500000 | 2015-11-18 | 2016-01-14 | 2016-01-21 |  | 2016-03-22 | Executed
| Navarre Beach Nourishment | D,C | Santa Rosa County | 8355034 | 2750000 | LATF | 37 20 2 423001 37350100 00 140126 16
| South Siesta Key Beach Nourishment | D,C | Sarasota County | 6761688 | 2750000 | LATF | 37 20 2 423001 37350100 00 140126 16
| South St. Lucie Beach Restoration | C | St. Lucie County | 27833.6
14BO2 | Broward County Shore Protection Project/ Segment II | C | Broward County | 2783569.2 | 2700000 | LATF | 37 20 2 423001 37350100 00 140126 16 | 2332029.06 | 2014-01-06 | 2015-10-09 | 2015-10-22 | 2016-01-06 | 2016-01-07 | Executed
| South Marco Island Nourishment | C | Collier County | 111904.6896 | 1500000 | GR | 37 10 1 000286 37350100 00 140126 16
| South Boca Raton Beach Nourishment | C | City of Boca Raton | 820375.251
| Central Boca Raton Beach Nourishment | C | City of Boca Raton | 3903637.4 | 1700000 | LATF | 37 20 2 423001 37350100 00 140126 16
| Hallandale Beach Nourishment | D | City of Hallandale | 367536.75
| Juno Beach Nourishment | D,C | Palm Beach County | 9125000
| Mid-Town Beach Nourishment | D,C | Town of Palm Beach | 7487604
15MI1_A1 | Bathtub/Sailfish Point | D,C | Martin County | 2800000 | 2800000 | GR | 37 10 1 000286 37350100 00 140126 16 | 1293910.2 |  | 2016-03-24 |  |  |  | In draft
| Brevard County Shore Protection Project/ Mid-Reach Segment | D,C | Brevard County | 1941387 | 1900000 | LATF | 37 20 2 423001 37350100 00 140126 16
| Flagler County Federal Feasibility Study | F,D | Flagler County | 337800
| Phipps Ocean Park Beach Nourishment | C | Town of Palm Beach | 6851793
| Perdido Key Beach Restoration | D,C | Escambia County | 4155244.3
| Rest Beach Nourishment | C | City of Key West | 438867
| Marathon Beaches Nourishment | C | City of Marathon | 26913
| South Ponte Vedra/Vilano Beach/Summerhaven Beach Restoration | F | St. Johns County | 306500 | 306500 | GR | 37 10 1 000286 37350100 00 140126 16
| Key Biscayne Beach Nourishment | C | Village of Key Biscayne | 1207500
| Coral Cove Park Dune Nourishment | C | Palm Beach County | 425000
| Southern Palm Beach Island Restoration | F,D | Palm Beach County | 172000
| Vero Beach Restoration | F | Indian River County | 50000
|  |  | Total | 100962865.3091 | 32106500
|  |  | Total Remaining |  |  |  |  | 32106500
Executed Contract
Contract in draft

## Post Construction Monitoring
Post Construction Monitoring 2yr. & 3rd year --Fund as GR
Contract Number | Project Name | Phase | Sponsor | Amount per LBR (State Share) | Amount Appropirated (State Share) | Amount to be Contracted (State Share) | 29 digit funding source code | Scope of Work Approval | Date Draft in Process | Date to Legal | Date Forwarded to Sponsor | Date Executed | Comments
1533954
| Venice Beach Nourishment/ Sarasota County Shore Protection Project |  | City of Venice | 265904.5908 | 265905
16SJ1 | St. Johns County Shore Protection Project |  | St. Johns County | 67518 | 67518 | 55065.31 | 37 10 1 000286 37350100 00 140126 16 | 2015-10-20 | 2015-11-02 |  | 2015-12-09 | 2016-01-28 | Executed
15SL4_A1 | Ft. Pierce Shore Protection Project |  | St. Lucie County | 135000 | 135000 | 71284.75 | 37 10 1 000286 37350100 00 140126 16 | 2016-02-12 | 2016-03-08 |  |  |  | In draft
| Brevard County Shore Protection Project/ North&South Reaches |  | Brevard County | 372143.88 | 372144 |  | 37 10 1 000286 37350100 00 140126 16
| Jupiter/Carlin Segment- Palm Beach County Shore Protection Project |  | Palm Beach County | 100000 | 100000 |  | 37 10 1 000286 37350100 00 140126 16
| South Amelia Island Beach Nourishment |  | DEP/Parks/SAISSA | 139509.18
| Upham Beach Groin Replacement |  | Pinellas County | 9200
| Longboat Key Beach Nourishment |  | Town of Longboat Key | 59204.0899
| Jupiter Island Beach Nourishment |  | Town of Jupiter Island | 46165 | 46165 |  | 37 10 1 000286 37350100 00 140126 16
| North Boca Raton Segment/ Palm Beach County Shore Protection Project |  | Palm Beach County | 127500 | 32000 |  | 37 10 1 000286 37350100 00 140126 16
| Pensacola Beach Nourishment |  | Santa Rosa Island Authority | 14975
| Wabasso Beach Restoration |  | Indian River County | 225000
| Collier County Beach Nourishment |  | Collier County | 152280.9
| Ocean Ridge Segment- Palm Beach CountyShore Protection Project |  | Palm Beach County | 51300 | 51300 |  | 37 10 1 000286 37350100 00 140126 16
| Martin County Shore Protection Project |  | Martin County | 342300 | 342300 |  | 37 10 1 000286 37350100 00 140126 16
16LE1 | Bonita Beach Nourishment |  | Lee County | 33910 | 33910 |  | 37 10 1 000286 37350100 00 140126 16 | 1992-11-02 | 2015-11-18 | 2016-01-14 | 2016-01-22 | 2016-03-22 | Executed
| South Siesta Key Beach Nourishment |  | Sarasota County | 123077
15SL3_A1 | South St. Lucie Beach Restoration |  | St. Lucie County | 239195 | 87712 | 141741.05 | 37 10 1 000286 37350100 00 140126 16 | 2016-02-23 | 2016-03-07 |  |  |  | In draft
| South Marco Island Nourishment |  | Collier County | 17038.08
| South Boca Raton Beach Nourishment |  | City of Boca Raton | 66015
| Central Boca Raton Beach Nourishment |  | City of Boca Raton | 5240.34
| Marathon Beaches Nourishment |  | City of Marathon | 5000
| Key Biscayne Beach Nourishment |  | Village of Key Biscayne | 87500
|  |  |  | 2684976.0607 | 1533954

## Inlet List
Inlets List | No appropriation for FY 15/16
Contract Number | Project Name | Phase | Sponsor | Amount per LBR (State Share) | Amount Appropirated (State Share) | Amount to be Contracted (State Share) | Scope of Work Approval | Date Draft in Process | Date Forwarded to Sponsor | Date Executed | Comments
| Port Canaveral IMP Implementation | D,C,M | Canaveral Port Authority | 160500
| Lake Worth IMP Implementation | M | Town of Palm Beach | 46500
| Longboat Pass IMP Implementation | D,C | WCIND, Town and County | 4963899.75
| St. Lucie Inlet IMP Implementation | C | Martin County | 1452828
| Port Everglades IMP Implementation | D | Broward County | 738750
| Ft. Pierce Inlet IMP Implementation | D | St. Lucie County | 675000
| South Lake Worth Inlet IMP Implementation | M | Palm Beach County | 53662
| Sebastian IMP Implementation | C,M | Sebastian Inlet District | 741000
| Boca Inlet IMP Implementation | C,M | City of Boca Raton | 384300
| Venice IMP Implementation | C,M | WCIND | 273750
| Big Carlos Pass Inlet Study | F | WCIND | 109500
| Southwest Gulf Coast Regional Inlet Study | F | WCIND | 187500
|  |  | Total | 9787189.75